## Sheet1
Task | Details | Guidance | Owner(s) | Days
Governance: must be complete before Phase 1 go-live |  | Click here to access the 111 implementation documents webpage
Hold 111 Online kick-off meeting | Overview of 111 Online programme, product demonstration, outline of work/responsibilities, discussion of local requirements and circumstances | We recommend inviting the following key stakeholders: Commissioner(s) who will lead 111OL implementation, DoS Leads who will update the directory for digital referrals, IUC representative with knowledge of the provider’s technical system | End user/NHS Digital | 1
Establish implementation working group | These will be the key personnel for executing the tasks and who submit their work to oversight by the relevant lead commissioner or board(s) in the local area | See requirements schedule: ' Assign team and map stakeholders' | End user | 3
Agree clinical governance arrangements and sign-off | Identify clinical leadership; complete any assessments of the product; establish an incident management log | See requirements schedule: 'Local End User and service responsibilities' See requirements schedule: STOP criteria and processes in Appendix B. EIA/QIAs to be produced locally. NHS Digital will produce a draft template soon. | End user | 2
Finalise information sharing arrangements | Update local privacy notices on 111 telephone provider sites regarding the 111 Online product; ensure that a summary of the data flows through online service are reviewed and approved by local Caldicott Guardian | See requirements schedule: 'Information Governance' | End user/NHS Digital | 2
Clinical sign-off | Clinical safety sign-off is needed because local commissioners choose how to map dispositions. For example, some may decide to map selected attend Emergency Department dispositions like Dx 02, 03, 89 to attend the UTC instead. |  | End user | 1
Create local SOP(s) for incident and complaints procedures | Outline procedures to handle patient complaints, technical failures, operational issues or clinical incidents | See requirements schedule: 'Monitoring and Incident Management' | End user | 3
Set-up emergency on-call rota | Who will be available in the event of a technical or clinical problem? |  | End user | 3
Sign End-User Agreement with NHS Digital | This must be done by a commissioner | End User agreement available on the documents webpage Ensure the stakeholders who will sign off the agreement are involved at the beginning of the project. | End user/NHS Digital | 1
Hold Go/No-Go call | Final check to ensure everything is ready; do this for each phase |  | End user/NHS Digital | 1
Go-live! |  |  | End user/NHS Digital
Schedule post-live meetings after every phase | NHS Digital recommends holding a post-live meeting one month after implementing each phase. NHSD project manager and a product expert will attend to discuss any issues or concerns. | see requirements schedule: 'Post implementation' | End user | 1
Phase 1: DoS work
Confirm with NHS Digital the CCGs adding 111 Online service | NHS Digital will update the website to accept users from these areas |  | End user | 1
Send NHS Digital the Service Unique Identifiers for services in the go-live area | NHS Digital will allow these services to appear to users in search results and will include the in test results | See Provision of Service UIDs for NHS 111 online document | End user | 2
Clean-up DoS listings so they are suitable for the public to view online | Profiles may contain acronyms that users will not understand, like GP OOH. Place to phone need phone numbers that are intended for public use. Places to visit should have complete addresses. | See requirements schedule: 'DoS look-ups and DoS Filtering', 'Working with the DoS for online' & 'Dispositions' | End user | 2
Add the appropriate text to the 'Public Facing Information' field | This will specify whether a user can visit this service or should phone. This is ignored if the service has been setup as an ITK service. | See requirements schedule: 'Working with the DoS for online' | End user | 15
Add 'Digital Referral' referral role to service that should be included in 111OL search results | All services tagged with this role are eligible to be shown to users in 111OL search results |  | End user | 3
Check DoS search results using automated tools including search results for boundary postcodes. | NHS Digital has built tools that let DoS leads quickly verify the services 111OL will return to users for all postcodes and dispositions and how results will appear on screen | See requirements schedule: 'Checking DoS results' DoS direct linking tool available on the documents webpage Ask NHS Digital to produce screenshots for each disposition's search results (both in-hours and out-of-hours) Overview of limiting DoS returns by CCG available on the documents webpage | End user/NHS Digital | 5.5
Troubleshoot and fix any DoS profiles that do not return correctly. | NHS Digital has provided a troubleshooting workflow to help identify issues in DoS profiling for 111 Online. | See Troubleshooting for DoS Leads on the documents webpage |  | 0.5
Inform implementation working group and NHS Digital that DoS is ready for 111 Online | Commissioners and NHS Digital must be satisfied that DoS profiling is complete |  | End user/NHS Digital | 1
Congratulations! New status: Live (Phase 1)
Phase 2: IUC-111OL connection
Decide which 111OL dispositions need a callback | In Phase 2 111OL users must be able to arrange a callback from the CAS. Commissioners may also decided to further customise the DoS to help manage urgent care workflows. For example, they could allow users to arrange a callback in order to book an urgent appointment with a GP. |  | End user | 4
Set up 111 Online clinical callback profile in DoS |  | See requirements schedule: 'Creating new DoS Profiles' | End user | 3.5
FIll in the ITK Testing Template provided | Each DoS Service ID needs to be supplied in advance, so it can be added to our ITK whitelist. This enables the 'book a call button' for that service. | See ITK Testing plan - Fill in the ITK Testing Template provided at the bottom of the sheet |  | 0.5
Ensure IUC system can receive referrals from 111 Online 111provider configuration has been done | Some IUC providers may need to configure their system to receive inbound referrals. They must also decide which queue will receive CAS referrals (usually nurses' queue) and prepare staff to handle these referrals. | See ITK Testing Plan for details on 111 Provider configuration requirements | End user | 8
Arrange Date to test ITK Messaging with 111 OL provider | Each service that receives ITK messages will need testing with each DX code they are profiled for. Ensure the testing session has: DoS support (to open /close services) Provider support (someone to action the messages) and 111 online support (to send the messages) | See requirements schedule: 'Checking ITK messages' See ITK Testing plan available on the documents webpage | End user/NHS Digital | 8
Congratulations! New status: Live (Phase 2)
Phase 3: Full integration of UEC services
Engage with local providers about accepting patients from 111OL | Providers will want to establish how they will receive referrals and how many to expect |  | End user/NHS Digital | 3
Furnish NHS Digital with a referrals whitelist/ Fill in the ITK Testing Template provided | This is the list of endpoints that will receive patient referrals from 111OL: GP OOHs, dentists, UTCs, etc. 111 OL supports referrals delivered by both ITK and email. | See requirements schedule: 'Creating new DoS Profiles' See ITK Testing plan - Fill in the ITK Testing Template provided at the bottom of the sheet | End user | 2
Carry out any systems configurations needed to accept 111OL referrals | Endpoints that already receive ITK referrals from IUC should be ready for 111OL. Pre-testing work may be required for other providers. | See ITK Testing Plan for details on 111 Provider configuration requirements | End user/NHS Digital | 15
Arrange dates for testing message transmission with providers | Schedule testing with NHS Digital. Any failed tests will need to be retested | See requirements schedule: 'Checking ITK messages' See ITK Testing plan available on the documents webpage | End user/NHS Digital | 8
Congratulations! New status: Live (Phase 3)
Comms: variable by location
Tell NHSD to turn on IVR message and SMS capability | National IVR message will be switched on at go-live, Phase 1. Callers to 111 will hear a message in-queue (or can opt to receive a text message) about the new online option. This helps convert 111 users from telephone to online triage. |  | End user/NHS Digital | 1
Decide local comms approach | Areas can decide how softly or aggressively to announce the 111 Online service and whom their messages should target. |  | End user | 5
Contact Meg.Rowley@nhs.net for supporting materials from NHS Digital | NHSE and NHSD are producing text and visuals that CCGs can use in their marketing efforts |  | End user | 3